## Stakeholder Register
Stakeholder Analysis — Supply Chain Cost Optimization
These are proposed roles for a realistic hypothetical case, not verified people from an actual company. Validate roles, authority and engagement with the business owner in a live project.
ID | Stakeholder / Role | Type | Interest / Needs | Role / Purpose | Key Responsibilities | Decision Rights / Authority | Influence | Interest | Communication / Cadence | Key Risks / Concerns
STK-01 | Executive Sponsor (e.g., COO / VP Supply Chain) | Internal — Leadership | Wants measurable cost improvement without harming service, availability, quality or margin. | Owns strategic direction and business case. | Confirm objectives and success measures; approve scope and major changes; provide resources/access; resolve escalations; review final business case. | Approves mandate, material scope changes and high-level recommendation direction. | High | High | Kick-off, milestone reviews, final readout; escalation as needed. | Savings may be overstated; cost reduction may damage service.
STK-02 | Business Owner / Supply Chain Director | Internal — Business owner | Wants end-to-end cost and performance improvements that are operationally useful. | Accountable owner of the business problem and outcome. | Clarify pain points; prioritize questions; define trade-offs; validate operational plausibility; nominate SMEs; assign action owners. | Owns business requirements and prioritization; recommends acceptance to sponsor. | High | High | Weekly workshops and milestone reviews. | A local saving could increase total end-to-end cost.
STK-03 | Supply Chain / Logistics Operations Manager | Internal — Operational SME | Needs practical improvements to shipping, carrier, dispatch and logistics performance. | Explains current operational process and tests feasibility. | Explain shipment planning, dispatch, carrier selection and delivery exceptions; validate delay/cost interpretation; assess feasibility. | Confirms operational facts and feasibility; action authority follows governance. | High | High | Weekly during discovery/validation. | Dataset may omit contracts, exceptions, seasonality and real constraints.
STK-04 | Procurement / Strategic Sourcing Manager | Internal — Functional SME | Wants lower total purchasing cost while maintaining quality and continuity. | Explains supplier terms, price, lead time and sourcing constraints. | Validate spend/unit-cost definitions; explain terms, MOQ, lead-time variability, supplier concentration and quality constraints. | Validates procurement rules; recommends sourcing actions within authority. | High | High | Review at discovery and procurement finding validation. | Lower unit price may increase quality risk or total landed cost.
STK-05 | Inventory / Demand Planning Manager | Internal — Functional SME | Wants balanced working capital, stock availability and replenishment performance. | Validates inventory, reorder and planning-policy findings. | Explain forecasts, safety stock, reorder rules, service levels and product criticality; validate target assumptions; assess inventory changes. | Validates planning assumptions; recommends policy changes through governance. | High | High | Weekly during inventory analysis. | Inventory reduction could create stockouts; snapshots may not reflect average stock.
STK-06 | Finance Business Partner / Cost Controller | Internal — Financial control | Needs credible, reconcilable savings and transparent financial assumptions. | Ensures KPI and benefit calculations are financially meaningful. | Confirm cost/revenue/profit definitions; distinguish realized savings from estimates; check baseline, double counting and implementation cost. | Validates financial methodology; formal sign-off depends on policy. | High | High | KPI review and final financial validation. | Dataset totals may not reconcile to finance systems; gross savings may omit costs.
STK-07 | Data Owner / ERP or Supply Chain Systems Owner | Internal — Data governance | Needs accurate, traceable and authorized use of data. | Confirms source, definitions, lineage, access and limitations. | Identify authoritative sources; explain keys, refresh and business rules; approve access; clarify retention and data-use policy. | Approves access/source decisions within delegated governance authority. | High | Medium | Data discovery at start and when issues arise. | Missing fields, duplicate keys, unclear meanings, unauthorized disclosure.
STK-08 | Data Analyst / BI Developer | Internal — Delivery team | Needs clear requirements, reliable model and reproducible analytics. | Builds data preparation, analysis and dashboard outputs. | Profile data; document transformations; build measures/visuals; reconcile totals; test filters; version assets; explain limitations and fix defects. | Owns technical design within agreed requirements; does not unilaterally redefine business KPIs. | Medium | High | Weekly or per sprint; frequent during build. | Unclear requirements cause rework; visuals can imply unsupported causation.
STK-09 | Warehouse / Facility Manager | Internal — Operational SME | Needs throughput, capacity and inventory accuracy improvements. | Explains local facility context and validates facility-level patterns. | Confirm capacity and utilization meanings; explain storage, labor, shifts, downtime and local exceptions. | Confirms facility facts; local implementation authority varies. | Medium | High | Facility review when relevant findings arise. | Low utilization may reflect seasonality, product mix or incomplete data.
STK-10 | Supplier / Vendor Representative | External — Third party | Wants stable demand, fair terms and clear service expectations. | May provide evidence on lead time, capacity, price and service. | Clarify supplier-side constraints through authorized channels; provide supporting data; review proposed changes where appropriate. | No authority over internal project scope; internal procurement owns commercial decisions. | Medium | Medium | As needed, procurement-led. | Commercial sensitivity, biased self-reporting and confidentiality risk.
STK-11 | Customer Service / Sales Operations | Internal — Customer impact SME | Wants on-time fulfilment and customer experience protected. | Explains customer commitments and consequences of service trade-offs. | Validate service definitions and priority segments; explain expedite costs, penalties, cancellations and complaints. | Validates customer constraints; commercial authority follows company policy. | Medium | High | At KPI design and recommendation validation. | Cost reductions may increase delays, penalties or churn.
STK-12 | Project Manager / Delivery Lead (if assigned) | Internal — Project governance | Wants delivery within agreed scope, timeline and quality. | Coordinates work, dependencies, risks, decisions and governance. | Maintain plan, RAID/action/decision logs; track dependencies; facilitate reviews; escalate scope/time/resource conflicts. | Manages delivery within delegated authority; sponsor owns strategic scope decisions. | High | High | Weekly status; immediate escalation when needed. | Unclear ownership, delayed decisions and scope creep.
STK-13 | Compliance / Information Security (as applicable) | Internal — Control function | Needs data handling and sharing to comply with policy. | Advises on confidentiality, approved tools and publication controls. | Review access, retention, masking, external tools and sharing when data is sensitive. | Authority depends on organization policy and data classification. | Medium–High | Medium | At start and before external publication if relevant. | Sensitive information or employer data could be exposed publicly.
STK-14 | Portfolio Reviewer / Hiring Manager (portfolio context) | External — Evaluation audience | Wants evidence of BA thinking, traceability, quality and communication. | Evaluates the portfolio artifact, not the hypothetical operation. | Review problem framing, stakeholder logic, requirements-to-KPI traceability, evidence, assumptions and recommendations. | No authority over hypothetical business; may evaluate portfolio quality. | Medium | Medium | GitHub README, final report and walkthrough. | Project may imply real-company access or unsupported impact.

## Power-Interest Matrix
Power–Interest Matrix
Initial classification only. Reassess after stakeholder discovery. Manage closely = high power/high interest; keep satisfied = high power/lower interest; keep informed = lower power/high interest; monitor = lower power/lower interest.
Stakeholder / Role | Influence / Power | Interest | Quadrant | Engagement Approach
Executive Sponsor | High | High | Manage closely | Decision gates, concise business case, escalation
Business Owner / Supply Chain Director | High | High | Manage closely | Discovery, prioritization, validation, acceptance
Logistics Operations Manager | High | High | Manage closely | Weekly operational validation
Procurement Manager | High | High | Manage closely | Review landed cost, supplier risk and sourcing constraints
Inventory / Demand Planning Manager | High | High | Manage closely | Validate replenishment assumptions and service guardrails
Finance Business Partner | High | High | Manage closely | Agree baseline, definitions and savings methodology
Data Owner / Systems Owner | High | Medium | Keep satisfied | Consult early on access, lineage and source-of-truth
Data Analyst / BI Developer | Medium | High | Collaborate / keep informed | Frequent requirement and prototype reviews
Warehouse / Facility Manager | Medium | High | Consult / keep informed | Consult on facility-level findings
Supplier / Vendor Representative | Medium | Medium | Monitor / consult selectively | Procurement-led contact only
Customer Service / Sales Operations | Medium | High | Keep informed / consult | Review customer impact and service guardrails
Project Manager / Delivery Lead | High | High | Manage closely | Weekly plan, risks, decisions and dependencies
Compliance / Information Security | Medium–High | Medium | Keep satisfied | Consult when data handling/publication requires it
Portfolio Reviewer / Hiring Manager | Medium | Medium | Keep informed | Clear README, report and evidence-led walkthrough

## RACI Matrix
RACI — Roles and Accountability
R = Responsible (does work); A = Accountable (final owner); C = Consulted (two-way input); I = Informed (one-way update). Proposed starting point only; confirm authority in a real organization and aim for one A per activity.
Activity / Deliverable | Sponsor | Business Owner | Operations | Procurement | Inventory Planning | Finance | Data Owner | Analyst / BI | Project Lead | Customer Service | Compliance
Confirm problem, objectives and success measures | A | R | C | C | C | C | I | C | R | C | I
Approve scope and material scope changes | A | R | C | C | C | C | I | I | R | I | I
Identify stakeholders and engagement plan | I | A | C | C | C | C | C | C | R | C | I
Define business terms and KPI specifications | I | A | R | R | R | R | C | R | C | C | I
Confirm source, lineage, access and limitations | I | C | C | C | C | C | A/R | R | C | I | C
Profile data and document quality issues | I | C | C | C | C | C | C | A/R | I | I | I
Build analysis, model and dashboard | I | C | C | C | C | C | C | A/R | C | C | I
Validate operational interpretation / root-cause hypotheses | I | A | R | R | R | C | C | R | C | C | I
Validate cost definitions and savings method | I | C | C | C | C | A/R | C | R | I | I | I
Review service and customer impact | I | A | R | C | R | C | I | R | I | R | I
Prioritize recommendations and action owners | A | R | R | R | R | C | I | C | C | C | I
Approve final business case / recommendation direction | A | R | C | C | C | C | I | C | C | C | I
Prepare final report and present findings | I | A | C | C | C | C | I | R | R | C | I
Track benefits after implementation (if implemented) | I | A | R | R | R | R | I | C | C | C | I